## WBS Spreadsheet
Smart Complaint Management System WBS Spreadsheet
Milestone | Task ID | Task | Owner | Duration (days) | Notes
1. Project Planning | 1.1 | Requirement Gathering | Project Manager | 7 | Includes stakeholder meetings
| 1.2 | Budget Planning | Finance Manager | 5 | Budget approval required
| 1.3 | Schedule Development | Project Manager | 3 | Create project timeline
2. System Design | 2.1 | Functional Design | IT Department | 10 | Define systemarchitecture
| 2.2 | Technical Specifications | IT Department | 7 | Technical documentation
3. System Development | 3.1 | Front-End Development | Development Team | 15 | Develop UI for system
| 3.2 | Back-End Development | Development Team | 20 | Build core system functions
| 3.3 | Database Development | Development Team | 10 | Configure database
4. Testing and Quality Assurance | 4.1 | System Testing | QA Team | 5 | Test system functionality
| 4.2 | User Acceptance Testing | End Users | 3 | Ensure user feedback is collected
5. Implementation and Deployment | 5.1 | Deploy System | IT Department | 3 | Deploy to all regions
| 5.2 | User Training | HR/Training Team | 2 | Train all customer service staff
| 5.3 | Go Live | IT Department | 1 | System goes live
6. Post-Implementation Support | 6.1 | Monitoring and Optimization | IT Department | 10 | Ongoing system monitoring
| 6.2 | Feedback and Improvements | Customer Service Team | 5 | Gather feedback and improve