## Gantt Chart
Gantt Chart
TITLE: Smart Complaint Management System | [6 empty] | COMPANY NAME: |  |  |  |  | Xcc Telecom
PROJECT MANAGER: Ahmed Ramadan Mahmoud | [6 empty] | CREATION DATE: |  |  |  |  | 11/2024
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [14 empty] | PHASE THREE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | MARCH | [22 empty] | APRIL | [21 empty] | MAY | [20 empty] | JUNE
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | [6 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
1.1 | Requirement Gathering | Business Analyst | Nov 1, 2024 | Nov 7, 2024 |  | 0%
1.2 | Budget Planning | Finance Manager | Nov 8, 2024 | Nov 12, 2024 |  | 0% | bar: MARCH M 15 to MARCH F 26
1.3 | Schedule Development | Project Manager | Nov 13, 2024 | Nov 15, 2024 |  | 0%
2 | System Design
2.1 | Functional Design | System Architect | Nov 16, 2024 | Nov 25, 2024 | 10 | 0% | bar: APRIL M 12 to APRIL W 14
2.2 | Technical Specifications | System Architect | Nov 26, 2024 | Des 2, 2024 | 7 | 0%
3 | System Development
3.1 | Front-End Development | Development Team Lead | Dec 3, 2024 | Dec 17, 2024 | 15 | 0% | bar: MAY M 3 to MAY F 14
3.2 | Back-End Development | Development Team Lead | Dec18, 2024 | Jan 6, 2025 | 20 | 0% | bar: MAY F 28
3.3 | Database Development | Development Team Lead | Dec 18, 2024 | Dec 31, 2024 | 10 | 0%
4 | Testing and Quality Assurance
3.1 | System Testing | QA Manager | Jan 7, 2025 | Jan 11, 2025 | 5 | 0% | bar: MAY M 3 to MAY F 14
3.2 | User Acceptance Testing | QA Manager | Jan 12, 2025 | Jan 14 2025 | 3 | 0% | bar: MAY F 28
5 | Implementation and Deployment
3.1 | Deploy System | IT Manager | Jan 15, 2025 | Jan 17, 2025 | 3 | 0% | bar: MAY M 3 to MAY F 14
3.2 | User Training | Development Team Lead | Jan 18, 2025 | Jan 19, 2025 | 2 | 0% | bar: MAY F 28
3.3 | Go Live | Development Team Lead | Jan20, 2025 | Jan 20, 2025 | 1 | 0%
5 | Post-Implementation Support
3.1 | Monitoring and Optimization | 2025-01-21 | 2025-01-21 | 2025-01-31 | 10 | 0% | bar: MAY M 3 to MAY F 14
3.2 | Feedback and Improvements | 2025-02-01 | 2025-02-01 | Feb 5, 2025 | 5 | 0% | bar: MAY F 28