## Precedence
Activity ID | Activity | Precedence | Duration (Days)
A | Finalize project scope, objectives, and deliverables | - | 5
B | Gather detailed requirements | A | 7
C | Document all technical and functional requirements | B | 5
D | Create Wireframes and Mockups | C | 7
E | Design Review with Klar | D | 3
F | Finalize UI/UX Design | E | 5
G | Define AI and Product Recommendation Engine Architecture | C | 7
H | Design Backend Infrastructure | G | 7
I | Database Schema Design | H | 5
J | Develop Skin Analysis Algorithm | G | 10
K | Train AI Model with Data | J | 8
L | Test AI for Product Recommendation Accuracy | K | 5
M | Build Product Database | I | 7
N | Integrate Product Information | M | 5
O | Implement Product Matching Algorithm | N | 6
P | Develop Android App | F | 10
Q | Develop iOS App | F | 10
R | User Interface Implementation | F | 8
S | Build User Registration and Authentication System | I | 7
T | Implement AI Processing System | S | 7
U | Create Product Recommendation Engine | T | 8
V | Test Skin Analysis on Sample Data | L | 5
W | Validate Product Recommendations | V | 4
X | Review AI Output with Dermatologists | W | 6
Y | Usability Testing for User Interface | R | 5
Z | Functional Testing for Core Features | Y | 5
AA | Functional Testing for Core Features | U | 4
AB | Penetration Testing | AA | 5