## Project Budget
Budget: Project Smart Complaint Management System & Training
[7 empty] | TARGET BUDGET | ACTUAL/ FINAL SPEND | UNDER/ OVER
[7 empty] | 40000 | 0 | 40000
LABOR | MATERIALS |  |  |  |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE DETAILS | HOURS | RATE | UNITS | $/UNIT
Milestone 1: Project Planning
Task 1: Requirement Gathering | Project Manager | 7 | 50 |  |  |  | 350 |  | -350
Task 2:Budget Planning | Project Manager | 5 | 60 |  |  |  | 300 |  | -300
Task 3:Schedule Development | Project Manager | 3 | 50 |  |  |  | 150 |  | -150
-- | [5 empty] | Total | 800 | 0
Milestone 2:System Design
Task 1: Functional Design | IT Department | 10 | 70 |  |  |  | 700 |  | 700
Task 2: Technical Specifications | IT Department | 7 | 60 |  |  |  | 420 |  | -420
-- | [5 empty] | Total | 1120 | 0
Milestone 3:System Development
Task 1: Front-End Development | Development Team | 15 | 80 |  |  |  | 1200 |  | -1200
Task 2:Back-End Development | Development Team | 20 | 80 |  |  |  | 1600 |  | -1600
Task 3:Database Development | Development Team | 10 | 80 |  |  |  | 800 |  | -800
-- | [5 empty] | Total | 3600 | 0
Milestone 4:Testing and Quality Assurance
Task 1: System Testing | QA Team | 5 | 50 |  |  |  | 250
Task 2:User Acceptance Testing | End Users | 3 | 50 |  |  |  | 150
[6 empty] | Total | 400 | 0
Milestone 5:Implementation and Deployment
Task 1: Deploy System | IT Department | 3 | 100 |  |  |  | 300 |  | -300
Task 2:User Training | HR/Training Team | 2 | 50 |  |  |  | 100 |  | -100
Task 3:Go Live | IT Department | 1 | 200 |  |  |  | 200 |  | -200
[6 empty] | Total | 600
Milestone 6:Post-Implementation Support
Task 1: Monitoring and Optimization | IT Department | 10 | 60 |  |  |  | 600 |  | -600
Task 2:Feedback and Improvements | Customer Service Team | 5 | 50 |  |  |  | 250 |  | -250
-- | [5 empty] | Total | 850 | 0
Reserve buffer | [6 empty] | 2500
TOTAL | [6 empty] | 9870 | 0