## Comm Plan
Project Smart Complaint Management System Project : Employee Training Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Project Team | Project Planning Meeting | Daily | Project Manager | Every day at 10am | In Person / Video Call | Ensure project planning, updates on deliverables and timelines | [link to meeting agenda and notes] | Check-in on progress, highlight any issues.
Development Team | System Design Review | Weekly | Project Manager | Every Monday | Video Call / Email | Review the system design and receive feedback | [Link to Design Documents] | Ensure alignment on system development steps.
Finance Manager | Budget Update | Bi-weekly | Project Manager | Every two weeks | Email / Video Call | Share progress on project budget, actual spend vs forecast | [Link to Budget Reports] | Discuss any adjustments in costs.
IT Department | System Testing Review | Bi-weekly | QA Lead | Every second Friday | Video Call / Report | Review results of system testing and issues tracking | [Link to Testing Results] | Address bugs or technical issues promptly.
Customer Service Team | Training Coordination | As Needed | HR/Training Lead | During Implementation | Email / In Person | Coordinate training sessions for customer service representatives | [Link to Training Schedule] | Ensure training covers all required modules.
CEO and Senior Leadership | Project Milestone Updates | Monthly | Project Manager | End of each month | Video Call / Presentation | Provide high-level updates on project progress and key milestones | [Link to Executive Summary] | Focus on risks, achievements, and timeline adherence.
End Users (Test Group) | User Acceptance Testing Feedback | Post-Testing | Project Manager | After Testing Phase | Email / Survey | Collect feedback on user experience and system functionality | [Link to Feedback Form] | Use feedback for final improvements.
Stakeholders (Xcc Telecom) | Project Status Report | Monthly | Project Manager | End of each month | Email / Presentation | Keep stakeholders informed of overall project status | [Link to Project Dashboard] | Include key risks, financial status, and timeline updates.

## Comm Plan Template 2 (hidden)
Project Communication Plan
Project Title:
Project Manager:
Executive Sponsor:
Principal Stakeholder:
Date:
Deliverable Info (What) | Recipient(s) (Who) | Delivery Method(s) (How) | Schedule (When) | Who's Responsible? (Owner)
Project Information
Project Status
Agenda Minutes
Timeline Update
Project Updates Action Item Status
Project Risks

## Comm Plan Template 3 (hidden)
| Purpose | Medium | Frequency | Audience
Kickoff meeting
Project team meetings
Check-ins/ meeting recap
Project status meetings
UX design reviews