## Dashboard
Project Smart Complaint Management System : Operations & Training Plan
Description: This is a document resource overview for the Operations and Training plan for Xcc Telecom's Smart Complaint Management System.
Owner: Ahmed Ramadan Mahmoud
Status: Draft
Key Docs | Description
Project charter | An overview of the project, key elements and expectations
Statement of work | Identifies the work that is included in the project and the pricing that was quoted initially.
Risk management plan | Identifies the potential risks to the project, their likelihood, and how you plan to mitigate them if they become realized.
Schedule | Identifies the planned schedule as well as any changes through out the project lifecycle.
Budget | Identifies the planned budget as well as any over and under runs. Allows you to estimate the cost at completion.
Communication plan | Identifies how often, what type of communication method, and what information your stakeholders needs to know
Shared folder | Folder with all relevant documentation
RACI chart | Identifies who is responsible, accountable, consulted and informed within the project.
Note on A7: Add hyperlink to digital document, Project charter
Note on A8: Add hyperlink to digital document, Statement of work
Note on A9: Add hyperlink to digital document, risk management plan
Note on A13: Add hyperlink to a shared folder
Note on A14: Add hyperlink to RACI chart

## Project Schedule
Gantt Chart
TITLE: Smart Complaint Management System | [6 empty] | COMPANY NAME: |  |  |  |  | Xcc Telecom
PROJECT MANAGER: Ahmed Ramadan Mahmoud | [6 empty] | CREATION DATE: |  |  |  |  | 11/2024
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [14 empty] | PHASE THREE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | MARCH | [22 empty] | APRIL | [21 empty] | MAY | [20 empty] | JUNE
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | [6 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
1.1 | Requirement Gathering | Business Analyst | Nov 1, 2024 | Nov 7, 2024 |  | 0%
1.2 | Budget Planning | Finance Manager | Nov 8, 2024 | Nov 12, 2024 |  | 0% | bar: MARCH M 15 to MARCH F 26
1.3 | Schedule Development | Project Manager | Nov 13, 2024 | Nov 15, 2024 |  | 0%
2 | System Design
2.1 | Functional Design | System Architect | Nov 16, 2024 | Nov 25, 2024 | 10 | 0% | bar: APRIL M 12 to APRIL W 14
2.2 | Technical Specifications | System Architect | Nov 26, 2024 | Des 2, 2024 | 7 | 0%
3 | System Development
3.1 | Front-End Development | Development Team Lead | Dec 3, 2024 | Dec 17, 2024 | 15 | 0% | bar: MAY M 3 to MAY F 14
3.2 | Back-End Development | Development Team Lead | Dec18, 2024 | Jan 6, 2025 | 20 | 0% | bar: MAY F 28
3.3 | Database Development | Development Team Lead | Dec 18, 2024 | Dec 31, 2024 | 10 | 0%
4 | Testing and Quality Assurance
3.1 | System Testing | QA Manager | Jan 7, 2025 | Jan 11, 2025 | 5 | 0% | bar: MAY M 3 to MAY F 14
3.2 | User Acceptance Testing | QA Manager | Jan 12, 2025 | Jan 14 2025 | 3 | 0% | bar: MAY F 28
5 | Implementation and Deployment
3.1 | Deploy System | IT Manager | Jan 15, 2025 | Jan 17, 2025 | 3 | 0% | bar: MAY M 3 to MAY F 14
3.2 | User Training | Development Team Lead | Jan 18, 2025 | Jan 19, 2025 | 2 | 0% | bar: MAY F 28
3.3 | Go Live | Development Team Lead | Jan20, 2025 | Jan 20, 2025 | 1 | 0%
5 | Post-Implementation Support
3.1 | Monitoring and Optimization | 2025-01-21 | 2025-01-21 | 2025-01-31 | 10 | 0% | bar: MAY M 3 to MAY F 14
3.2 | Feedback and Improvements | 2025-02-01 | 2025-02-01 | Feb 5, 2025 | 5 | 0% | bar: MAY F 28

## Budget
Budget: Project Smart Complaint Management System & Training
[7 empty] | TARGET BUDGET | ACTUAL/ FINAL SPEND | UNDER/ OVER
[7 empty] | 40000 | 0 | 40000
LABOR | MATERIALS |  |  |  |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE DETAILS | HOURS | RATE | UNITS | $/UNIT
Milestone 1: Project Planning
Task 1: Requirement Gathering | Project Manager | 7 | 50 |  |  |  | 350 |  | -350
Task 2:Budget Planning | Project Manager | 5 | 60 |  |  |  | 300 |  | -300
Task 3:Schedule Development | Project Manager | 3 | 50 |  |  |  | 150 |  | -150
-- | [5 empty] | Total | 800 | 0
Milestone 2:System Design
Task 1: Functional Design | IT Department | 10 | 70 |  |  |  | 700 |  | 700
Task 2: Technical Specifications | IT Department | 7 | 60 |  |  |  | 420 |  | -420
-- | [5 empty] | Total | 1120 | 0
Milestone 3:System Development
Task 1: Front-End Development | Development Team | 15 | 80 |  |  |  | 1200 |  | -1200
Task 2:Back-End Development | Development Team | 20 | 80 |  |  |  | 1600 |  | -1600
Task 3:Database Development | Development Team | 10 | 80 |  |  |  | 800 |  | -800
-- | [5 empty] | Total | 3600 | 0
Milestone 4:Testing and Quality Assurance
Task 1: System Testing | QA Team | 5 | 50 |  |  |  | 250
Task 2:User Acceptance Testing | End Users | 3 | 50 |  |  |  | 150
[6 empty] | Total | 400 | 0
Milestone 5:Implementation and Deployment
Task 1: Deploy System | IT Department | 3 | 100 |  |  |  | 300 |  | -300
Task 2:User Training | HR/Training Team | 2 | 50 |  |  |  | 100 |  | -100
Task 3:Go Live | IT Department | 1 | 200 |  |  |  | 200 |  | -200
[6 empty] | Total | 600
Milestone 6:Post-Implementation Support
Task 1: Monitoring and Optimization | IT Department | 10 | 60 |  |  |  | 600 |  | -600
Task 2:Feedback and Improvements | Customer Service Team | 5 | 50 |  |  |  | 250 |  | -250
-- | [5 empty] | Total | 850 | 0
Reserve buffer | [6 empty] | 2500
TOTAL | [6 empty] | 9870 | 0

## Communication Plan
Project Smart Complaint Management System Project : Employee Training Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Project Team | Project Planning Meeting | Daily | Project Manager | Every day at 10am | In Person / Video Call | Ensure project planning, updates on deliverables and timelines | [link to meeting agenda and notes] | Check-in on progress, highlight any issues.
Development Team | System Design Review | Weekly | Project Manager | Every Monday | Video Call / Email | Review the system design and receive feedback | [Link to Design Documents] | Ensure alignment on system development steps.
Finance Manager | Budget Update | Bi-weekly | Project Manager | Every two weeks | Email / Video Call | Share progress on project budget, actual spend vs forecast | [Link to Budget Reports] | Discuss any adjustments in costs.
IT Department | System Testing Review | Bi-weekly | QA Lead | Every second Friday | Video Call / Report | Review results of system testing and issues tracking | [Link to Testing Results] | Address bugs or technical issues promptly.
Customer Service Team | Training Coordination | As Needed | HR/Training Lead | During Implementation | Email / In Person | Coordinate training sessions for customer service representatives | [Link to Training Schedule] | Ensure training covers all required modules.
CEO and Senior Leadership | Project Milestone Updates | Monthly | Project Manager | End of each month | Video Call / Presentation | Provide high-level updates on project progress and key milestones | [Link to Executive Summary] | Focus on risks, achievements, and timeline adherence.
End Users (Test Group) | User Acceptance Testing Feedback | Post-Testing | Project Manager | After Testing Phase | Email / Survey | Collect feedback on user experience and system functionality | [Link to Feedback Form] | Use feedback for final improvements.
Stakeholders (Xcc Telecom) | Project Status Report | Monthly | Project Manager | End of each month | Email / Presentation | Keep stakeholders informed of overall project status | [Link to Project Dashboard] | Include key risks, financial status, and timeline updates.